## Agent
USER AGENT
DATE | PAGE | FUNCTION | TEST DETAIL | RESULT | REMARKS
2020-09-01 | QUOTE DETAIL | DROPDOWN FILTERS | Testing all filters functioning well | TO DO
2020-09-01 | MY QUOTES | NUMBER OF BIDS UPDATE | Number of bids are increased live when new bid is entered | Y
2020-09-01 | NAVBAR ALERTS | ALERTS PUSHED LIVE | Alerts popped up live | TO DO
2020-09-03 | QUOTE DETAIL | ADD CLOSE QUOTE BUTTON | Add button to close quote | TO DO
2020-09-03 | QUOTES LIST | REDUCE ACTION BUTTON | Reduce or remove button to fit row height | y
2020-09-03 | EMAIL | EMAIL FORMAT | Open email client and shows quote+bid detail? | TO DO
2020-09-03 | NOTIFICATIONS | Check notification link | When bid is VOIDED by user | TO DO
2020-09-03 | NOTIFICATIONS | Check navbar and email | For Basic and premium plan user | TO DO
2020-09-03 | QUOTES LIST | Check filters | Check filters (default date puplish) | Y
2020-09-03 | CREATE QUOTE | Special cargo radio buttons | Check colours of special cargo (Y/N) |  | FIX REQUIRED Tooltip ? Icon not changed

## AIRLINE
USER AIRLINE
DATE | PAGE | FUNCTION | TEST DETAIL | RESULT Y/N | REMARKS
2020-09-01 | QUOTE DETAIL | Dropdowns & filters | Check all filters functioning correctly
2020-09-02 | QUOTES LIST | Data pushed live | Agent enters quote and same is displayed live on airline quotes list page | Y | highlight effect too short?
2020-09-02 | QUOTES LIST | Data pushed live | Agent closes manually his quote and same is pushed live on airline quotes list page | Y
2020-09-02 | QUOTES LIST | Data pushed live | Quote closed automatically by cron job and same displeyed live on airline quotes list view
2020-09-02 | MY BIDS | Ranking color pushed live | Change ranking color live when new bids are entered | Y
2020-09-02 | MY BIDS | Bid status pushed live | Change quote status live when quote is closed | TO DO
2020-09-02 | NAVBAR ALERTS | Alerts pushed live |  | TO DO
2020-09-02 | QUOTE DETAIL | Trying to bid on Closed Quote | When quote is closed same should appear on airline quote detail page and button shouldnt show possibility to bid again. | Y
2020-09-03 | CREATE BID | Remarks Field reduced | 12 carachters max | TO DO
2020-09-03 | QUOTES LIST | Different color visited rows | Visited Quotes rows show different colour | TO DO
2020-09-03 | BID DETAIL | Remove fields | Zip /Address and City on next row | TO DO
2020-09-03 | QUOTES LIST | Filters default | Published date sorted from most recent | TO DO
2020-09-03 | BID DETAIL | Move buttons | Buttons at the bottom of page when bid summary appears | TO DO
2020-09-03 | NUMBER OF BIDS | set max 1 bid per user | Check possibility to enter second bid (only possible when a previous bid has been canceled) | TO DO
2020-09-03 | NOTIFICATIONS | Check notification link | When bid is VOIDED by user | TO DO
2020-09-03 | NOTIFICATIONS | Check navbar and email | For Basic and premium plan user | TO DO
2020-09-03 | MY BIDS | Check bid is listed correctly | When airline user cancels and enters new bid same not showing | to fix | BUG

## ADMIN
USER ADMIN
DATE | PAGE | FUNCTION | TEST DETAIL | RESULT | REMARKS